## Sheet1
My GitHub Branch: |  | https://github.com/slacshan/MIDI-Projects.git
Day | hours
Week 1
2025-11-18 | 3 | Started research on the pic16f1788
2025-11-19 | 4 | Continued research and started the coding for the master and slave I2C send and recive (3 byte modification)
2025-11-20 | 7 | Started working on Eusart recive (MIDI) for the master
Week 2
2025-12-01 | 6.5 | continued the midi recive code (Issues with reciving the 3 bytes of midi individually)
2025-12-02 | 7 | continued the midi recive code (Issues with reciving the 3 bytes of midi individually)
2025-12-03 | 6 | Started working on sending midi via I2C after 3 bytes of Euart midi is recived, Soldered a master board to use
2025-12-04 | 6 | Started working on the Address filter for the midi to only send if master address matches the midi channel
2025-12-05 | 7 | Started working on note filter so only a certain selection of notes are sent and if they are out of range then no I2C is sent
2025-12-06 | 1.5 | Made my flow chart for the Master and Slave code I programed
Week 3
2025-12-08 | 6.5 | Finished the Note filter and started soldering slave boards
2025-12-09 | 6.5 | Soldered a 2nd slave board and worked on the Mosfet driver boards
2025-12-10 | 6.5 | Finished the Mosfet driver boards and the second slave board and started making cables
2025-12-11 | 11.25 | Helped jason and brandon troubleshoot slave issues in code, made I2C cables
2025-12-12 | 8.5 | Helped jason and brandon troubleshoot slave issues in code
Week4
2025-12-15 | 6.5 | Troubleshooting the code and making cables, practice presentation
2025-12-16 | 10.5 | made cables did a practice presentation and hooked everything up
2025-12-17 | 4:00 | writeup
TOTAL
104.25